## Sheet1
Epic | Epic | Epic | Epic | Epic | Epic | Epic
Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies. | US001 | Complete the Homepage for the Agile Manifesto | Design and implement a visually appealing homepage. Add an introduction to Agile and its history. Include navigation to other sections of the platform. | 3 | 1 | Agile
| US002 | Build the Agile Values and Principles section. | Create a page to display the four core Agile values. Implement an interactive feature to explain the 12 principles. Add examples to illustrate each value and principle. | 2 | 2 | Agile
| US003 | Develop the Resource Library. | Design a library for Agile practices (Scrum, Kanban, etc.). Include downloadable resources like templates and guides. Add search and filter functionality. | 5 | 3 | Agile
| US004 | Implement Collaboration Features and perform final testing | Develop a discussion forum for users. Enable users to comment on resources and principles. Implement user authentication for collaboration features. | 8 | 4 | Agile
Story | Subtasks
Design and implement a visually appealing homepage. Add an introduction to Agile and its history. Include navigation to other sections of the platform. | Create wireframes to outline the homepage layout. Develop the homepage using HTML and CSS. Add engaging animations with JavaScript. Conduct user testing and gather feedback.
Create a page to display the four core Agile values. Implement an interactive feature to explain the 12 principles. Add examples to illustrate each value and principle. | Design and develop a page to display the four Agile values. Implement interactive elements to explain the 12 principles dynamically. Add examples for each value and principle to enhance understanding. Test the page for usability and responsiveness. |  | Link - Jira Link
Design a library for Agile practices (Scrum, Kanban, etc.). Include downloadable resources like templates and guides. Add search and filter functionality. | Design the layout and structure of the resource library. Upload templates and guides for Agile practices. Implement search and filter features using JavaScript. Test the library for usability and functionality.
Develop a discussion forum for users. Enable users to comment on resources and principles. Implement user authentication for collaboration features. | Design the discussion forum layout and user interface. Develop backend APIs to handle forum posts and comments. Implement user authentication for secure access. Test the forum and commenting features for functionality.